## PIS 2014-2020
NATIONAL GOVERNMENT CONSTITUENCIES DEVELOPMENT FUND BOARD
NORTH HORR
PROJECT IMPLEMENTATION REPORT AS AT 30TH JUNE 2021
Financial year | Project name | Approved Activity | Estimated Cost | Amount Allocated | Completion Date | Implementation Status | Remarks
2014/2015 | Administration/ Recurrent Expenditure | CDF Administration, CDF Vehicle running and maintenance of office machines | 6536305 | 6536305 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Monitoring & Evaluation | Purchase of Fuel and other costs/Capacity Building/Committee Expenses | 3268152 | 3268152 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Bursary/ Mocks | Payment of fees for the needy students in secondary/Tertiary colleges | 25734600 | 25734600 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Bursary/ Mocks | Mocks/CATS | 1500000 | 1500000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Emergency Reserve | Emergency responses in the Constituency | 5400259 | 5400259 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Shurr Pry School | Construction of 1no. Classroom with 20 Lockers and Admin Blocks | 3200000 | 3200000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Turbi Nomadic Girls Pry Sch | Construction of Admin Block | 2000000 | 2000000 | 31st June 2015 | Complete | Complete and in use
2014/2015 | Ririba Girls Pry Sch | Construction of one staff Quarter | 1500000 | 1500000 | 32nd June 2015 | Complete | Complete and in use
2014/2015 | Balesa Saru Pry Sch | Construction one classroom and supply of 20 Lockers | 1400000 | 1400000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Garwole Pry Sch | Construction one classroom and supply of 20 Lockers | 1400000 | 1400000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Hilder Primary Sch | Construction of one classroom and Supply of 40 Lockers | 2600000 | 2600000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Rage Primary Sch | Construction of one Classroom and Supply of 20 Lockers & Admin Block | 3200000 | 3200000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Barambate Pry Sch | Construction one classroom and supply of 20 Lockers | 1400000 | 1400000 | 31st June 2015 | Complete | Complete and in use
2014/2015 | Gas Pry Sch | Construction one classroom and supply of 20 Lockers | 1400000 | 1400000 | 32nd June 2015 | Complete | Complete and in use
2014/2015 | Telesgaye Pry Sch | Construction one classroom and supply of 20 Lockers and Admin Block | 3600000 | 3600000 | 33rd June 2015 | Complete | Complete and in use
2014/2015 | Elbesso Pry Sch | Construction one classroom and supply of 20 Lockers | 1400000 | 1400000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Malabot Pry Sch | Construction of Girls Dormitory | 2400000 | 2400000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Hurri Hills Pry Sch | Purchase of 60 Lockers and assorted office Furniture | 500000 | 500000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Elgadhe Pry Sch | Construction of one Dormitory with 20 Double Decker beds and 4 inch mattresses | 3500000 | 3500000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Segel Pry Sch | Construction of two Classrooms and Supply of 40 Lockers | 2600000 | 2600000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Balesa Pry Sch | Completion of Admin Block | 600000 | 600000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Kalacha Pry Sch | Rehabilitation of Workshop hall | 837931 | 837931 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Hon. Isacko Memorial Sec Sch | Construction of Dormitory with 20 Double deckers with 4 inch mattresses | 4000000 | 4000000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Dukana Secondary Sch | Construction of one Classroom and supply of 20 Lockers & completion of Admin Block | 3400000 | 3400000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Dr Godana Memorial Boys Sec Sch | Construction of one classroom and supply of 20 Lockers | 1400000 | 1400000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Maikona Girls Sec Sch | Construction of one Library Block | 2253615 | 2253615 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Russo Mixed Day Sec Sch | Construction one Laboratory Block | 4000000 | 4000000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | North Horr Girls Sec Sch | Construction of Dining hall and Kitchen | 3200000 | 3200000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Gas Dispensary Modern Maternity Blcok | Completion of Maternity Block- 7 Bed Capacity | 2700000 | 2700000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Sports | Support sport Torunament in the Constituency | 2178768 | 2178768 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Environmental Activities | Qorqa Primary Sch-School fencing to Facilitate tree planting | 1000000 | 1000000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Environmental Activities | Dukana Sec Sch-Fencing to Facilitate tree planting | 1178768 | 1178768 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Others | Buluk AP Line- Fixing Burglar proofing window and doors | 150000 | 150000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Others | CDF Motor Vehicle- Toyota Landcruiser Hardtop four Wheel drive | 7000000 | 7000000 | 30th June 2015 | Complete | Complete and in use
2014/2015 | Consitituency Audit | Constituency Audit | 500000 | 500000 | 30th June 2015 | Complete | Complete and in use
SUB TOTAL |  |  | 108938398 | 108938398
2015/2016 | Admin/Recurrent | CDF Administration, CDF Vehicle running and maintenance of office machines | 6927283 | 6927283 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Monitoring & Evaluation | Purchase of Fuel and other costs/Capacity Building/Committee Expenses | 3463641 | 3463641 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Bursaries/Social Security Programmes | Payment of fees for the needy students in secondary/Tertiary colleges | 28863677 | 28863677 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Sports | Support Sports Torunament in the Constituency | 2309094 | 2309094 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Environmental Activities | Support Environmental Protection in the Constituency | 2309094 | 2309094 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Emergency | Support unforeseen emergency expenses in the Constituency | 5767647 | 5767647 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Balesa Saru Pry Sch | Construction of one Classroom and supply of 20 Lockers and staff Quarters | 3600000 | 3600000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Garwole Pry Sch | Construction of one Classroom and supply of 20 Lockers | 1400000 | 1400000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Barambate Pry Sch | Construction of one Classroom and supply of 20 Lockers | 1400000 | 1400000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Forole Pry Sch | Renovation of Dormitory and Construction of Administration Block | 3000000 | 3000000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | El-Besso Pry Sch | Construction of one Classroom and supply of 20 Lockers | 1400000 | 1400000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | North Horr Pry Sch | Renovation of 8 Classrooms, Kitchen and Dining Hall | 5000000 | 5000000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Malabot Pry Sch | Completion of Dormitory Ongoing and Construction of Staff Quarters | 4000000 | 4000000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Ririba Girls Pry Sch | Completion of staff Quarters-ongoing | 500000 | 500000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Turbi Nomadic Girls Pry Sch | Construction of one Classroom | 1200000 | 1200000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Shurr Pry Sch | Construction of staff Quarters | 2400000 | 2400000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Bishop Cavallera Pry Sch | Renovation of 6 Classrooms | 2000000 | 2000000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Segel Primary Sch | Construction of staff Quarters | 2000000 | 2000000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Kalacha Pry Sch | Renovation of 5 Classrooms | 2000000 | 2000000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Maikona Pry Sch | Renovation of 4 Classrooms | 1500000 | 1500000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Dukana Pry Sch | Renovation of 4 Classrooms | 1800000 | 1800000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Balesa Primary Sch | Renovation of 4 Classrooms | 1600000 | 1600000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | El-hadi Pry Sch | Fencing School Compound | 1852087 | 1852087 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Gas Pry Sch | Renovation of 4 Classrooms | 1600000 | 1600000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Hurri Hills Pry Sch | Construction of staff Quarters | 2200000 | 2200000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Water Projects | Kalacha Nomadic Girls- Installation of Solar water pumps and water storage tanks | 1500000 | 1500000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Maikona Girls Sec Sch | Completion of Library Block | 2500000 | 2500000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | North Horr Girls Sec Sch | Completion of fencing School Compound and Construction of Kitchen/stores | 4362185 | 4362185 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Dukana High Sch | Completion of Administration Block-ongoing and Construction of staff Quarters | 3500000 | 3500000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Russo Mixed Day Sec Sch | Completion of Laboratory -topup,ongoing and construction of staff quarters | 3200000 | 3200000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Illeret Secondary Sch | Construction of two Classrooms and supply of 40 lockers | 2800000 | 2800000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Hon. Isacko Memorial High Sch | Construction of Dormitory with 20 Double Decker Beds and 4 inch Mattresses | 4000000 | 4000000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Chalbi Boys High Sch | Completion of fencing of school compound | 2000000 | 2000000 | 30th June 2016 | Complete | Complete and in use
2015/2016 | Mallalba, Shurr and Marime Radio Calls | Purchase and Installation of radio calls | 1000000 | 1000000 | 30th June 2016 | Complete | Complete and in use
SUB TOTAL |  |  | 114954708 | 114954708
2016/2017 | Administration/ Recurrent Expenditure | CDF Administration, CDF Vehicle running and maintenance of office machines | 4913793 | 4913793 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Monitoring and Evaluation/ Capacity Building | To support Committee expenses/Goods and services and Capacity Building | 2456897 | 2456897 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Sports | Support Constituency Sports Tournamanet/Trophies and awards | 1637931 | 1637931 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Environmental Activities | Dukana High Sch-Fencing and Beaconing to protect natural trees | 600000 | 600000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Environmental Activities | Chalbi Muslim Primary School- fencing and beaconing works | 1037931 | 1037931 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Emergency Reserves | To Cater for unforeseen emergency Expenses | 4094827.59 | 4094827.59 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Bursary Secondary Schools | Payment of bursary to needy student | 16163793 | 16163793 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Bursary Tertiary Schools | Payment of bursary to needy student | 9000000 | 9000000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Mocks and Cats | Supply of Mocks, Cats and revision books to primary schools within the constituency. | 1500000 | 1500000 | 30th June 2017 | Complete | Funds Reallocated to Revision Materials for Schools
2016/2017 | Shurr AP Line | Construction of AP Houses | 2000000 | 2000000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Forole Primary school | Assorted office furniture (10 lockers, 10 chairs and 1 wall ward-robe for administration block and 100 desks for classrooms | 1200000 | 1200000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Chalbi Primary school | Renovation of 8 classrooms- 4 classes roofing, painting, window/doors repair - Ksh. 800,000 & 4 floors/doors repair, walling and painting - Ksh. 800,000 | 1600000 | 1600000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Kalacha Primary school | Renovation of 4 classrooms each at Ksh. 500,000 - roofing, floors, windows, walling and painting. | 2000000 | 2000000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | El-Gadhe Primary school | Renovations of 7 classrooms and administration block each at Ksh. 200,000 - painting and flooring | 1600000 | 1600000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Ririba Girls Primary school | Fencing/beaconing | 1400000 | 1400000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | El-Hadi Primary school | Renovations of 8 classrooms each at Ksh. 200,000 - painting and flooring | 1600000 | 1600000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Dukana Primary school | Renovations of 4 classrooms each at Ksh. 400,000 - flooring, roofing, walling, and painting | 1600000 | 1600000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Balesa-Saru Primary school | Fencing/beaconing | 1400000 | 1400000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Helmer Girls Primary school | Construction of library block | 3000000 | 3000000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | El-Besso Primary school | Construction of staff house | 2100000 | 2100000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Ruso Primary school | Fencing/beaconing | 1400000 | 1400000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Gas Primary school | Fence repair (replacing of wooden polls with metallic polls and gate repair at Ksh. 1,000,000) and dining hall renovations - wall repair, dining hall furniture - 10 tables and 20 forms; and replace 5 dormitory doors with metalic doors and 2 washroom doors with wooden ones at Ksh. 1,000,000 | 2000000 | 2000000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Shurr Primary school | Construction of 1 administration block | 2200000 | 2200000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Bishop Cavallera Primary school | Construction of 1 classroom at Ksh. 1,100,000 with 20 lockers at Ksh 100,000. | 1200000 | 1200000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Turbi Primary school | Construction of administration block | 2000000 | 2000000 | 30th June 2017 | Complete | Funds reallocated to Balesa and Balesa Saru Primary School for fencing works.
2016/2017 | Burgabo Primary school | Construction of 2 classrooms each at Ksh 1,200,000 with 40 lockers at Ksh. 200,000. | 2600000 | 2600000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Segel Primary school | Construction of 1 classroom at Ksh. 1,100,000 with 20 lockers at Ksh 100,000. | 1200000 | 1200000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Bubisa Primary school | Renovation of 4 classrooms- floors repair each at Ksh. 200,000 each,Renovation of dormitory- 1 dorm floor, repair 4 windows and painting at Ksh. 400,000 and Renovation of dining hall & kitchen- flooring, windows repair, painting & replacement of chimney at Ksh. 400,000 | 1600000 | 1600000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Maikona Girls Secondary school | Construction of 1 dormitory at Ksh. 3,500,000, 20 double decker beds and 40 mattresses at Ksh. 500,000. | 4000000 | 4000000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | North-Horr Boys Secondary school | Renovation of dining hall/kitchen - flooring and painting of DH/kitchen at Ksh. 500,000 and furniture (15 tables and 30 forms at Ksh. 700,000) | 1200000 | 1200000 | 30th June 2017 | Complete | Complete and in use
2016/2017 | Illeret D.O's office | Construction of Residential House for the ACC at Illeret | 1591379.13 | 1591379.13 | 30th June 2017 | Complete | Complete and in use
SUB TOTAL |  | TOTAL | 81896551.72 | 81896551.72
2017/2018 | Administration/ Recurrent Expenditure | NGCDF Administration, NGCDF Vehicle running and maintenance of office machines | 5891379.31 | 5891379.31 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Monitoring and Evaluation/Capacity Building | For Monitoring and Evaluation of CDF Projects and Capacity Building of PMCS/NGCDFCs | 2945689.66 | 2945689.66 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Bursary/Social Security Programmes | To Pay School fees for Orphans and Needy students in the Constituency | 31786206.88 | 31786206.88 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Strategic Plan | To Meet the Costs of prepraring strategic plan for the Constituency | 1500000 | 3300000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Emergency Activities | To cater for unforeseen Costs in the Constituency | 5137931.03 | 5137931.03 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Environmental Activities | To Complete 950m Fencing works and beaconing to protect natural trees from deforestation at Qorqa Pry | 1736206.9 | 1736206.9 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Sports Activities | Purchase of Sport Kits, balls and uniforms for football teams | 1736206.9 | 1736206.9 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Chalbi Muslim Pry School | Completion fencing of 750metres with metallic poles,barbed wire and chain links | 1200000 | 1200000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Ruso Primary School | Completion fencing of 600 metres with metallic poles,barbed wire and chain links | 1000000 | 1000000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Forole Primary School | Completion of Purchase of Furniture-50 desks for Ksh 300,000, 10 Lockers for Ksh 85000, 10 Chairs for Ksh 30,000, One wall Wardrobe for Administration Block for Kshs 169,482.75 | 584482.75 | 584482.75 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Barambate Primary School | Construction of 1No. Classroom Ksh 1250000 and Purchase of 20 Desks at Ksh 150000 | 1400000 | 1400000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Bubisa Primary School | Wiring and Installation of Solar Panels and Batteries | 500000 | 500000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Bishop Cavallera Primary School | Construction of 2 Double door VIP Latrines | 1000000 | 1000000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | North Horr Primary School | Renovation of Staff Quarters; repair of floors; walls;roofing and painting works | 1500000 | 1500000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | North Horr Boys Secondary School | Renovation of dining hall;floors,walls,doors,windows,roofing and finishes | 1600000 | 1600000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Kalacha Girls High School | Construction of Staff Houses | 4800000 | 2400000 | 30th June 2018 | Complete | In Progress; 2.4 Million re-allocated to Strategic Plan (1.8m) and Ksh 0.6m to Balesa Saru Pry Sch
2017/2018 | Kalacha Girls High School | Construction of 3 Double door VIP Latrines | 1500000 | 1500000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Kalacha Girls High School | Construction of Dining Hall and Kitchen | 6500000 | 6500000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Kalacha Girls High School | Installation of Solar Panels and Systems | 2200000 | 2200000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Kalacha Girls High School | Installation of Water Systems | 1200000 | 1200000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Chalbi High School | Construction of One Dormitory | 4200000 | 4200000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | North Horr Girls Secondary School | Construction of One Dormitory | 5500000 | 5500000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Illeret D.O's Residence | Completion of two Bedroom and sitting room house for District Officer; roofing walling;floors and Paint works | 1700000 | 1700000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | North Horr Technical Training Institute | Electrical Connections (Ksh 2.2m);Water systems Connection (Ksh 1.6m); Two Double Door VIP Latrines (Ksh 1m) | 4800000 | 4800000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Maikona Girls Sec Sch | Installation of Solar Panels and Systems | 3500000 | 3500000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | North Horr Technical Training Institute | Fencing Works | 3000000 | 3000000 | 30th June 2018 | Complete | Complete and in use
2017/2018 | Ririba Girls Boarding Primary | Fencing Works | 0 | 600000 | 30th June 2018 | Complete | Complete and in use
SUB TOTAL |  | TOTAL | 98418103.43 | 98418103.43
2018/2019 | Administration/ Recurrent Expenditure | NGCDF Administration, NGCDF Vehicle running and maintenance of office machines | 6542452.53 | 6542452.53 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Monitoring and Evaluation/Capacity Building | For Monitoring and Evaluation of CDF Projects and Capacity Building of PMCS/NGCDFCs | 3271226.27 | 3271226.27 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Bursary/Social Security Programmes | To Pay School fees for Orphans and Needy students in the Constituency | 35924369.43 | 35924369.43 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Emergency Activities | To cater for unforeseen Costs in the Constituency | 5738993.45 | 5738993.45 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Environmental Activities | To Complete 950m Fencing works and beaconing to protect natural trees from deforestation at Qorqa Pry | 2180817.51 | 2180817.51 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Sports Activities | Purchase of Sport Kits, balls and uniforms for football teams | 2180817.51 | 2180817.51 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Baqaqa primary school | Construction of 2 no. Two door VIP latrines | 1000000 | 1000000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Barambate Primary school | Construction of 1 no. classroom for Ksh 1,580,000 and supply of 20 desks for Ksh 120,000 | 1700000 | 1700000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Barambate Primary school | Completion of a classroom facial board and painting works | 300000 | 300000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Balesa-Saru Primary School | Construction of 1 no. classroom for Ksh 1,580,000 and supply of 20 desks for 120,000 | 1700000 | 1700000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Bubisa Primary School | Installation of solar systems on five classrooms; Two Dormitories and one Dining hall; 9 panels, 6 Batteries; 5 inverters, 5 charge controllers and wiring works | 1816978.69 | 0 | 30th June 2019 | Complete | Re-allocated
2018/2019 | Bishop Cavallera Primary School | Fencing works; using metallic posts, barbed wire and chain links(500metres size) | 0 | 916978.69 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Kalacha Girls High School | Wiring and solar installation works; two classrooms, science laboratory and administration block | 0 | 900000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Gas Primary School | Wiring and Solar Installation works: 5 Classrooms; One Administration Block | 3100000 | 0 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Gas Primary School | Wiring and Solar Installation works: 5 Classrooms; One Administration Block | 0 | 1600000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Turbi High school | Installation of water systems; 8km piping works for Kshs. 1,260,000 and purchase of two 10,000 litres water tanks for Kshs.240,000 | 0 | 1500000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Malabot Primary school | Construction of 3 no. Two door VIP latrines | 1500000 | 1500000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | El-Isacko Mala primary school | Rehabilitation and Conversion of a dormitory i.e flooring,plastering,wall repairs, doors and windows fixing into three unit staff house and a washroom | 1500000 | 1500000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Qorqa Primary school | Renovation works and Supplies: Six metallic doors for Dormitory and Six Metallic doors for classrooms Ksh 120,000.00; Five flush doors for Toilets for Ksh 90,000; Large Metallic Cupboard for computer Tablets Ksh 170,000; Five Wooden Cabinet Tables for Ksh 120,000;Ten Chairs for Ksh 60,000; Forty 3.6* medium size Mattresses for Ksh 240,000;Forty Solar Batteries for Ksh 1200,000 | 2000000 | 800000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Turbi Nomadic Girls Primary School | Construction of 1 no. 2-bed room staff house (Ksh. 2.8 million) with installation of solar systems; 2 panels; 1 inverter; 1 charge controller; 2 batteries for Ksh. 400,000 and construction of septic tank and drainage pipes for Ksh 1 million. | 4200000 | 0 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Segel Primary school | Fencing using metallic posts, barbed wire/chain links to protect the school environment from livestock and protect trees 1500 Metres | 1685220.13 | 1685220.13 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Dukana Primary school | Construction of administration block; Slabbing, Walling; Roofing; Plastering and finishes | 2500000 | 2500000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Balesa Primary school | Renovation of 3 no. classrooms with tiling of the floors/corridor; Doors/Windows fixing, Plastering and wall repairs | 3000000 | 3000000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Illeret Primary school | Fencing works with metallic posts, barbed wires and chain link for the school compound 750m long. | 1500000 | 0 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Kalacha Girls High school | Construction of 1 no. classroom at Ksh 1,580,000 and supply of 20 lockers for Ksh 120,000 | 1700000 | 1700000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Kalacha Girls High school | Construction of one Administration blocks for Ksh 4,802,000 and supply of office furniture; 12 Tables for 288,000, 15 Chairs for 90,000, Six Cabinet for 720,000. | 5900000 | 5900000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Chalbi High school | Completion of 1 no. dormitory Ksh 1,000,000 and supply of 40 double decker beds for Ksh 520,000 and 80-3*4’’ medium size mattresses for Ksh 480,000.00 | 2000000 | 2000000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Ruso Mixed Secondary school | Fencing of the School compound using barbed wires, Chain link and Metallic posts 1300 meters | 3500000 | 3500000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Turbi High school | Construction of 1 no. classroom for Ksh 1,480,000 and supply of 20 lockers for Ksh 120,000, construction of 1 no. 2-bed room staff house for Ksh 280,000.00 | 4400000 | 4400000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Turbi High school | Construction of Administration block; foundation, slabs and superstructure walling | 0 | 1400000 | 30th June 2020 | Complete | Complete and in use
2018/2019 | Chalbi High School | Construction of 1 No. classroom for Ksh 1,480,000 and supply of 20 lockers for Ksh 120,000 | 1600000 | 1600000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Shurr AP line | Construction of 1 no. staff house phase 2 (Ksh. 1.8 million), solar installation on staff house (Ksh. 1.5 million) and construction of 1 no. Two Door VIP latrine | 3800000 | 3800000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | North Horr Technical Training Institute | Construction of 1 no. Two-bed room staff house | 2800000 | 2800000 | 30th June 2019 | Complete | Complete and in use
2018/2019 | Ririba Girls Boarding Primary | Fencing works | 0 | 1200000 | 30th June 2019 | Complete | Complete and in use
SUB TOTAL |  |  | 109040875.52 | 104740875.52
2019/2020 | Employees Salaries | Payment of staff salaries and Gratuity | 3212400 | 3212400 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Employees NHIF | Payment of NHIF Deductions | 106800 | 106800 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Employees NSSF | Payment of NSSF Deductions | 161280 | 161280 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Committee Expenses | Payment of Committee sitting allowances, transport, conferences. | 1368000 | 1368000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Goods and Services | Purchase of fuel, repairs and maintenance, printing, stationery, telephone, travel and subsistence, office tea, Air time, Electricity, Rent, Bank charges, Postal charges, Insurance costs. | 3393583.45 | 3393583.45 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Committee Expenses | Payment of Committee sitting allowances, transport, conferences | 1036000 | 1036000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Goods and Services | Purchase of fuel, printing, stationery, telephone, travel and subsistence, office tea, Air time, Electricity, Rent, Bank charges, Postal charges, Insurance costs. | 1585031.72 | 1585031.72 | 30/06/2020 | Complete | Complete and in use
2019/2020 | NG-CDFC and PMC Capacity Building | Undertake Training of the NGCDFC Staffs, PMCs and NG-CDFCs on NG-CDF Operations, Cross cutting Issues and Capacity Building activities | 1500000 | 1500000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Emergency Reserve | Cater for any urgent and unforeseen activity in the constituency during the financial year | 7198241.38 | 7198241.38 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Bursary Tertiary Institutions | Payment of bursary to needy students in Tertiary Institutions | 10000000 | 10000000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Bursary Secondary Schools | Payment of bursary to needy students in Secondary Schools | 31138000 | 31138000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Sports Projects | Purchase of 12 Sport Skits for each of 20 Primary School @ Kshs 84,000 per School;Gas,El-Isako Mala, Shur, Bishop Cavballera, North Horr Pry, Ruso,Helmer girls,Chalbi Muslim, Balesa, Ririba Girls, El-hadi, Dukana, Qorqa, El-gadhe, Kalacha Nomadic,Maikona, Hurri Hills,Forole, Turbi nomadic and Bubisa: Purchase of 12 Sport Skits for each of 8 Sec School @ Kshs 77,000 per School; Schools- North Horr Boys, North Horr Girls, Ruso Mixed, Dukana High, Kalacha Girls High, Chalbi High, Maikona Girls and Hon Isacko Memorial; Purchase of Costumes for Music Festivals for 8 Secondary Schools @ Kshs 56,419.31 per school North Horr Boys, North Horr Girls, Ruso Mixed, Dukana High, Kalacha Girls High, Chalbi High, Maikona Girls and Hon Isacko Memorial. | 2747354.48 | 2747354.48 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Kalacha Nomadic Girls Primary School | Replacement of old dilapidated wooden fences for Ksh 247,354.48; Fencing using barbed wire, chain link and metallic posts1500 meters to completion for Ksh 2,200,000 | 2447354.48 | 2447354.48 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Balesa Saru Primary School | Purchase of 20 Wooden Desks . | 120000 | 120000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | El-Isako Mala Primary school | Construction of 1 No. staff house with two bedrooms, kitchen, sitting room and a bathroom;Foundation and Superstructure Walling | 1300000 | 1300000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Helmer Girls' Primary School | Fencing Works Covering 900m with Metallic posts, Chainlink and Barbed Wires to completion | 1500000 | 1500000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Maikona Primary School | Purchase of 20 Wooden Desks | 120000 | 120000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Ruso Primary School | Construction of 1 No. double door VIP pit latrine:pit digging, foundation slabbing up to roofing. | 440000 | 440000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Shankera Primary School | Purchase of 20 Wooden Desks | 120000 | 120000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | The Tiigo School | Construction of 1 No. 40 student Capacity Dormitotory @ Ksh 3,520,000 to completion and Equipping with 20 No. Double Decker Beds for 300,000 and 40 Pcs 3'' by 4'' Mattresses for Ksh 180,000. | 4000000 | 4000000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Kalacha Girls High School | Construction of a 48 student Capacity Dormitory for Kshs 4,224,000 to completion and Equipping with 24 No. Double Decker Beds for 360,000 and 48-3'' by 4'' mattresses for Ksh 216,000. | 4800000 | 4800000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Kalacha Girls High School | Equipping of the Science Laboratory with Lab Apparatus and Equipment. | 1000000 | 1000000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Kalacha Girls High School | Purchase of 40 Wooden Desks | 240000 | 240000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Turbi High School | Solar Installation on 2 No. Classrooms, 2 No. staff houses, 1 No. Administration , 1 No. Dormitory Block with 18 Solar Panels for Kshs 720,000; 6 Inverters for Kshs 150,000; 6 Charge Controllers for Kshs 150,000; 14 Batteries for 448,000 and wiring works for Kshs 1,032,000. | 2500000 | 2500000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Turbi High School | Construction of 1 No. staff house with two bedrooms, kitchen, sitting room and a bathroom to completion. | 2800000 | 2800000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Turbi High School | Completion of Administration Block ( Walling, Flooring, Fixing Doors and Windows, Roofing, Plastering and Painting)Comprising of Four Offices, Staffroom and a store for Kshs 3,600,000 and Purchase of Furniture for Administration Block: 7 Tables for Kshs 105,000; 14 Chairs for Kshs 70,000 and Two Safety Cabinets for Kshs 225,000 | 4100000 | 4100000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Balesa Saru -Goth Biresa Security Road | Opening Up of new Security Road covering 22 KM; Bush Clearing and Removal of Boulders to Completion. | 3000000 | 3000000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Forole-Ulani Chabich Security Road | Opening Up of new Security Road covering 25 KM; Heavy Bush Clearing and Removal of Boulders to Completion. | 4500000 | 4500000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Gas-Qete Security Road | Opening Up of new Security Road covering 16 KM; Bush Clearing and Removal of Boulders to Completion. | 2800000 | 2800000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Illeret Police Post | Renovation of 1 No. 4 roomed staff house: Flooring, Walling, Roofing, windows repair, Fixing of 3 steel doors & Painting Works to completion. | 1500000 | 1500000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Segel-Chira Tone Security Road | Opening Up of new Security Road covering 22 KM; Bush Clearing and Removal of Boulders to Completion. | 3000000 | 3000000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Shurr Adminstration Police Line | Bush clearing and Piping of Water to staff houses to completion: Distance 2Km for Kshs 1,400,000; Construction of Circular Washing Slab for kshs 200,000 and Installation of One Low Level 10,000 Litres Plastic water Tank for Kshs 200,000. | 1800000 | 1800000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Shurr Adminstration Police Line | Fencing works covering 1.5 Km with metallic posts, barbed wire and chain link for Kshs 2,000,000 to completion and Construction of Two gates for Kshs 240,000 to completion | 2240000 | 2240000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Purchase of NG-CDF Branded Revision Text Books | Purchase and Distribution of Branded Revision Text Books for Std 7 and 8 Pupils in 20 Primary Schools @ Kshs 152,174 per School:Gas,El-Isako Mala, Shur, Bishop Cavballera,North Horr Pry, Ruso, Helmergirls, Chalbi Muslim, Balesa, Ririba Girls, El-hadi, Dukana, Qorqa, El-gadhe, Kalacha Nomadic, Maikona, Hurri Hills,Forole, Turbi nomadic and Bubisa:Revision Books are Revision Top Mark Series for Mathematics, English, Science, Business Studies, Chemistry, Physics, Biology, Agriculture, History and Government. | 3500703.45 | 3500703.45 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Quality Assurance for Schools | Facilitate Termly Quality Assurance Programmes in all Secondary Schools and all Primary Schools in the Constituency to Improve Schools Performance. | 3100000 | 3100000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | NGCDF Motor Vehicle | Purchase of a Landcruiser Pick Up 5,700,000; Fixation of Bullbars;rear seats,frame and canopy 800,000. | 6500000 | 6500000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Balesa Saru Primary School | Construction of 1 No. Classroom for Ksh 1,580,000 to completion. | 1580000 | 1580000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Maikona Primary School | Construction of 1 No. Classroom for Ksh 1,480,000 to completion | 1480000 | 1480000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Shankera Primary School | Construction of 1 No. Classroom for Ksh 1,480,000 to completion | 1480000 | 1480000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Kalacha Girls High School | Construction of 2 No. Classroom for Ksh 3,160,000 to completion | 3160000 | 3160000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Chalbi Muslim Primary School | Completion of Fencing works covering 600m with Chain Link, Barbed wires and Metallic Posts. | 1000000 | 1000000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Qorqa primary school | Repairs for 6 Classrooms and 1 No. Dormitory : Replace 6 Classroom's wooden doors with steel doors and the Dormitory door with steel door@ Kshs 45,000 inlcussive of labour and tranbsport costs and Kshs 10,495.86 per door fixing works. | 332975.18 | 332975.18 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Ruso Primary School | Partition/Separate and repair the Primary and Secondary School Fence covering 600m with metallic posts, barbed wire and chainlink to reduce obstruction of access to adjacent water points to completion. | 1000000 | 1000000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | North Horr Boys' Secondary School | Demolition and Re-construction of 4 No. Classrooms; Foundation and Superstructure walling. | 1800000 | 1800000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | North Horr Technical Training Institute | Renovation of Old staff House: Partitioning into Three rooms, Ceiling works, wiring works with electrical fittings and fixing doors to completion. | 2000000 | 2000000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | North Horr Technical Training Institute | Piping of water to the staff Houses covering 600m Distance for Kshs 800,000; Construction of Circular Slab for Ksh 100,000; Installation of 1 No. Low level 5,000 litres plastic water Tank for Ksh 100,000 and 1 No. High Level 5000 litres Plastic water Tank for Kshs 200,000 all to completion. | 1200000 | 1200000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Shurr Adminstration Police Line | Bush Clearing Works for Kshs 1,260,000 to Completion. | 1260000 | 1260000 | 30/06/2020 | Complete | Complete and in use
2019/2020 | Kalacha Nomadic Girls Primary School | Construction of gate pillars and re-fixing metallic door and Painting works for Ksh 200,000 to protect the school environment from livestock and protect trees. | 200000 | 200000 | 30/06/2020 | Complete | Complete and in use
TOTAL |  |  | 137367724.14 | 137367724.14